## Charter
Odoo Procure-to-Ship: Project Charter
Item | Detail
Project | Odoo Procure-to-Ship Case Study
Project lead | Sawandi Kirby
Company (fictional) | Hearth & Desk Supply Co., Pompano Beach FL
System | Odoo 20 trial: hearth-desk-supply-co.odoo.com (Inventory, Purchase, Manufacturing, Sales, Accounting)
Objective | Run procure-to-ship end to end for 7 customers and 5 vendors inside the Odoo trial, then deliver exports, a KPI dashboard and a public repo by 10/21.
In scope | Purchasing, manufacturing, shipping and carrier assignment, accounts payable
Out of scope | Payroll, CRM
Constraints | Trial expires 10/22/2026 and the database is deleted after capture. Vendor lead times compressed to 1-5 days so every receipt lands inside the trial.
Success criteria | Every sales order shipped. Both open vendor bills paid before export. KPIs reported against baseline. Repo Odoo-Procure-to-Ship-Case-Study pushed by 10/21.
Start / finish | Start 10/8/2026. Planned finish 10/21/2026. Buffer day 10/22.
Baseline source | Important_Plans\Odoo_Procurement_Planning_Case_Study_Design_2026-10-08.docx, with vendor-confirmed PO dates from 10/9
Method note | Disruptions in this project are designed scenarios. The responses, RAID logging and status reporting are done as events happen.

## Milestones
Milestones: Baseline vs Actual
ID | Milestone | Owner | Baseline | Forecast | Actual | Variance (days) | Status | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22
M1 | Customers + wave 1 SOs entered, POs confirmed to all 5 vendors | Sales / Purchasing | 2026-10-09 |  | 2026-10-09 | 0 | Done
M2 | Fastline + Packwell received, bills posted | Purchasing / AP | 2026-10-10 |  | 2026-10-10 | 0 | Done
M3 | Ironcrest received + bill, Cable Tray MO produced | Purchasing / Manufacturing | 2026-10-12 |  | 2026-10-12 | 0 | Done
M4 | Wave 2 SOs (4) confirmed | Sales | 2026-10-12 |  | 2026-10-12 | 0 | Done
M5 | Brightform received, Laptop Riser MO produced, Replenishment rerun | Purchasing / Manufacturing | 2026-10-13 |  | 2026-10-13 | 0 | Done
M6 | Greenline received in full | Purchasing | 2026-10-14 | 2026-10-16 | 2026-10-16 | 2 | Done
M7 | Remaining MOs complete (Desk Organizer, Monitor Stand) | Manufacturing | 2026-10-15 |  | 2026-10-15 | 0 | Done
M8 | All SOs shipped, carrier assignment done | Shipping | 2026-10-19 | 2026-10-19 | 2026-10-19 | 0 | Done
M9 | Vendor bills paid, exports + KPI dashboard | AP / Analytics | 2026-10-20 |  | 2026-10-20 | 0 | Done
M10 | Repo pushed, Odoo database deleted | Project lead | 2026-10-21 | 2026-10-22 | 2026-10-22 | 1 | Done
Trial ends
Legend
Baseline date
Actual, on time or early
Actual late, or forecast slip
Variance uses Actual when filled, otherwise Forecast. Positive = days late.

## RAID
RAID Log: Risks, Assumptions, Issues, Decisions
ID | Type | Date raised | Description | Impact | Response | Owner | Status
R1 | Risk | 2026-10-08 | Trial expires 10/22. Any slip past 10/21 risks losing the database before exports. | High | Exports scheduled 10/20, buffer day 10/22, screenshots captured at each milestone. | Project lead | Open
R2 | Risk | 2026-10-09 | Greenline has the longest lead time (5 days) and is the only source for its components. | Medium | Watch the 10/14 due date. If late, request a partial shipment and reschedule the dependent MO. | Purchasing | Closed (became I2)
A1 | Assumption | 2026-10-08 | Vendor lead times compressed from 21/14/10/5/3 days to 5/3/2/1/1 so all receipts land inside the trial. | Low | Stated in the case study writeup. | Project lead | Accepted
A2 | Assumption | 2026-10-08 | Coastal Express only serves FL, GA, NC and SC. Out-of-region orders need another carrier. | Low | Applied at carrier assignment in M8. 10/18: S00005 (KS) was booked on Coastal first; Odoo returned no Coastal option for a Kansas address, so it was rebooked on Bluepeak Freight. | Shipping | Accepted
D1 | Decision | 2026-10-09 | Order finished-goods reorder rules first so component demand traces back to MOs. | Medium | MOs WH/MO/00001-00004 created before component POs. | Project lead | Closed
D2 | Decision | 2026-10-09 | Vendor-confirmed dates: Ironcrest 10/12, Brightform 10/13, Fastline + Packwell 10/10, Greenline 10/14. | Medium | Written on PO lines and stock moves. | Purchasing | Closed
D3 | Decision | 2026-10-10 | Net 30 payment terms on all 5 vendors. Fastline + Packwell bills due 11/9. | Low | Bills reset to draft, term set, reposted. | AP | Closed
D4 | Decision | 2026-10-10 | Keep Odoo's 6% purchase tax so bills match the POs. | Low | One-line change if reversed. | AP | Closed
D5 | Decision | 2026-10-10 | Pay the Fastline + Packwell bills on 10/20 before exports, so AP data shows paid and unpaid side by side. | Low | Scheduled in M9. Paid 10/20: BILL/2026/10/0001 $139.75 and BILL/2026/10/0002 $250.69; 0003 and 0004 stay open (due 11/11, 11/12). | AP | Closed
I1 | Issue | 2026-10-13 | WH/MO/00004 posting error: components consumed (22 riser plates, 44 support arms, 44 hinge pins, 88 pads, 22 boxes) with 0 Laptop Risers recorded. MO cancelled. | Medium | Same-day fix: inventory adjustment returned the components, replacement WH/MO/00005 produced 22. Check finished qty before marking an MO done. | Manufacturing | Closed
D6 | Decision | 2026-10-13 | Replenishment rerun ordered Desk Organizer x11 (WH/MO/00006) and Cable Tray x12 (WH/MO/00007). | Medium | Cable Tray components on hand. Desk Organizer waits on Greenline bamboo panels due 10/14, adding to R2. | Purchasing / Manufacturing | Closed
I2 | Issue | 2026-10-14 | Greenline missed its 10/14 delivery. Partial delivery 10/15 (WH/IN/00001): 50 of 74 bamboo panels, 48 of 72 shelf boards. Remaining 24 + 24 on backorder WH/IN/00006, due 10/16. | Medium | Received the partial 10/15. It covered all open Desk Organizer and Monitor Stand MOs, so M7 finished on its 10/15 baseline; the backorder refills stock. Backorder WH/IN/00006 received in full 10/16 (24 + 24); M6 closed 2 days late. | Purchasing | Closed
D7 | Decision | 2026-10-18 | Out-of-region carrier: Bluepeak Freight for S00005 (KS) and S00006 (TN), the lowest cost serving those states ($19.18 and $33.48 vs Summit Parcel $25.32 and $43.52). S00007 (MI) goes on Summit Parcel to keep a second out-of-region carrier active. | Low | Carrier mix costs more on S00007; explained in status report #2. Cost comparison reported in status report #2. | Shipping | Closed
I3 | Issue | 2026-10-20 | P00001 (Greenline) was received in full (WH/IN/00001 partial 10/15, backorder WH/IN/00006 10/16) but no vendor bill was entered. Odoo shows the PO as Waiting Bills; 4 of 5 POs are billed. Found 10/20 during the M9 export review. | Medium | Enter and post the Greenline bill 10/21, matched to P00001 and both receipts, with Net 30 like the other four. Check every PO's billing status before close-out. Fixed 10/22: BILL/2026/10/0005 entered and posted for $1,039.86, 100% matched to P00001 and both receipts, Net 30 (due 11/21). All 5 POs now billed. | AP | Closed

## KPIs
KPI Dashboard
KPI | Value | Formula
Vendor on-time rate | 80% | Receipts on or before expected date / receipts so far
Vendor fill rate | 98.22% | Qty received on first receipt / qty ordered, received POs only
Schedule variance (avg days) | 0.3 | Average of Milestones variance column (positive = late)
Customer OTIF | 100% | SOs shipped complete and on or before promised date / SOs shipped
Order cycle time (avg days) | 7.6667 | Ship date minus confirm date, averaged over shipped SOs
Vendor Receipts
PO | Vendor | Expected | Received | Qty ordered | Qty received (first receipt) | On time (1/0) | Fill rate
P00001 | Greenline | 2026-10-14 | 2026-10-15 | 146 | 98 | 0 | 67.12%
P00002 | Ironcrest | 2026-10-12 | 2026-10-12 | 305 | 305 | 1 | 100%
P00003 | Brightform | 2026-10-13 | 2026-10-13 | 290 | 290 | 1 | 100%
P00004 | Fastline | 2026-10-10 | 2026-10-10 | 1744 | 1744 | 1 | 100%
P00005 | Packwell | 2026-10-10 | 2026-10-10 | 215 | 215 | 1 | 100%
Customer Orders
SO | Customer | Confirmed | Promised | Shipped | Shipped complete (Y/N) | OTIF (1/0) | Cycle time (days)
S00001 | Coastal Workspace Outfitters | 2026-10-09 | 2026-10-19 | 2026-10-17 | Y | 1 | 8
S00002 | Peachtree Office Interiors | 2026-10-09 | 2026-10-19 | 2026-10-17 | Y | 1 | 8
S00003 | Blue Ridge Learning Supply | 2026-10-09 | 2026-10-19 | 2026-10-17 | Y | 1 | 8
S00004 | Lowcountry Coworking Co. | 2026-10-09 | 2026-10-19 | 2026-10-18 | Y | 1 | 9
S00005 | Prairie Desk & Chair | 2026-10-09 | 2026-10-19 | 2026-10-18 | Y | 1 | 9
S00006 | Volunteer State Business Supply | 2026-10-12 | 2026-10-19 | 2026-10-18 | Y | 1 | 6
S00007 | Lakeshore Remote Works | 2026-10-12 | 2026-10-19 | 2026-10-19 | Y | 1 | 7
S00008 | Coastal Workspace Outfitters | 2026-10-12 | 2026-10-19 | 2026-10-19 | Y | 1 | 7
S00009 | Blue Ridge Learning Supply | 2026-10-12 | 2026-10-19 | 2026-10-19 | Y | 1 | 7
Wave 2 SOs confirmed 10/12 (M4).

## Dashboard
Procure-to-Ship KPI Dashboard
Source: Odoo exports 10/20/2026 (Dashboard_Data). Every value is a formula.
Avg PO cycle time (days) | Vendor on-time rate | MO schedule adherence | Avg shipping cost per order
3.2 | 80% | 100% | 22.7044
Confirm to full receipt | First receipt by confirmed date | Done MOs finished by baseline | All 9 deliveries

## Dashboard_Data
Purchase orders | [11 empty] | Receipts by vendor
po | vendor | confirmed | vendor_confirmed_due | fully_received | qty_ordered | qty_received | amount_untaxed | amount_total | cycle_days | on_time_first_receipt |  | Vendor | On time | Late
P00001 | Greenline Bamboo Supply | 2026-10-09 | 2026-10-14 | 2026-10-16 | 146 | 146 | 981 | 1039.86 | 7 | 0 |  | Greenline Bamboo Supply | 0 | 2
P00002 | Ironcrest Metalworks | 2026-10-09 | 2026-10-12 | 2026-10-12 | 305 | 305 | 1089.2 | 1154.55 | 3 | 1 |  | Ironcrest Metalworks | 1 | 0
P00003 | Brightform Aluminum | 2026-10-09 | 2026-10-13 | 2026-10-13 | 290 | 290 | 921.8 | 977.11 | 4 | 1 |  | Brightform Aluminum | 1 | 0
P00004 | Fastline Industrial | 2026-10-09 | 2026-10-10 | 2026-10-10 | 1744 | 1744 | 131.84 | 139.75 | 1 | 1 |  | Fastline Industrial | 1 | 0
P00005 | Packwell Packaging | 2026-10-09 | 2026-10-10 | 2026-10-10 | 215 | 215 | 236.5 | 250.69 | 1 | 1 |  | Packwell Packaging | 1 | 0
Receipts | [11 empty] | Shipping cost by carrier
receipt | po | vendor | due | received | qty_received | backorder_of | days_vs_due | on_time |  |  |  | Carrier | Orders | Avg cost per order
WH/IN/00001 | P00001 | Greenline Bamboo Supply | 2026-10-14 | 2026-10-15 | 98 |  | 1 | 0 |  |  |  | Coastal Express | 6 | 13.5
WH/IN/00002 | P00002 | Ironcrest Metalworks | 2026-10-12 | 2026-10-12 | 305 |  | 0 | 1 |  |  |  | Bluepeak Freight | 2 | 26.33
WH/IN/00003 | P00003 | Brightform Aluminum | 2026-10-13 | 2026-10-13 | 290 |  | 0 | 1 |  |  |  | Summit Parcel | 1 | 70.68
WH/IN/00004 | P00004 | Fastline Industrial | 2026-10-10 | 2026-10-10 | 1744 |  | 0 | 1
WH/IN/00005 | P00005 | Packwell Packaging | 2026-10-10 | 2026-10-10 | 215 |  | 0 | 1
WH/IN/00006 | P00001 | Greenline Bamboo Supply | 2026-10-14 | 2026-10-16 | 48 | WH/IN/00001 | 2 | 0
Manufacturing orders (planned finish = milestone baseline)
mo | product | qty_planned | qty_produced | state | started | finished | planned_finish | baseline_milestone | days_vs_plan | on_plan | lead_days
WH/MO/00001 | [FG-001] Desk Organizer | 24 | 24 | done | 2026-10-09 | 2026-10-15 | 2026-10-15 | M7 | 0 | 1 | 6
WH/MO/00002 | [FG-002] Monitor Stand | 22 | 22 | done | 2026-10-09 | 2026-10-15 | 2026-10-15 | M7 | 0 | 1 | 6
WH/MO/00003 | [FG-003] Cable Tray | 27 | 27 | done | 2026-10-09 | 2026-10-12 | 2026-10-12 | M3 | 0 | 1 | 3
WH/MO/00004 | [FG-004] Laptop Riser | 22 | 0 | cancel | 2026-10-09 | 2026-10-13 | 2026-10-13 | M5 (cancelled, I1) | #N/A |  | #N/A
WH/MO/00005 | [FG-004] Laptop Riser | 22 | 22 | done | 2026-10-13 | 2026-10-13 | 2026-10-13 | M5 (replaces 00004) | 0 | 1 | 0
WH/MO/00006 | [FG-001] Desk Organizer | 11 | 11 | done | 2026-10-13 | 2026-10-15 | 2026-10-15 | M7 | 0 | 1 | 2
WH/MO/00007 | [FG-003] Cable Tray | 12 | 12 | done | 2026-10-13 | 2026-10-15 | 2026-10-15 | M7 | 0 | 1 | 2
Deliveries
delivery | so | customer | ship_to_state | carrier | weight_lb | shipping_cost | shipped
WH/OUT/00001 | S00001 | Coastal Workspace Outfitters | FL | Coastal Express | 20.4 | 13.5 | 2026-10-17
WH/OUT/00002 | S00002 | Peachtree Office Interiors | GA | Coastal Express | 32.5 | 13.5 | 2026-10-17
WH/OUT/00003 | S00003 | Blue Ridge Learning Supply | NC | Coastal Express | 20.2 | 13.5 | 2026-10-17
WH/OUT/00004 | S00004 | Lowcountry Coworking Co. | SC | Coastal Express | 23.8 | 13.5 | 2026-10-18
WH/OUT/00005 | S00005 | Prairie Desk & Chair | KS | Bluepeak Freight | 13.8 | 19.18 | 2026-10-18
WH/OUT/00006 | S00006 | Volunteer State Business Supply | TN | Bluepeak Freight | 26.8 | 33.48 | 2026-10-18
WH/OUT/00007 | S00007 | Lakeshore Remote Works | MI | Summit Parcel | 46.2 | 70.68 | 2026-10-19
WH/OUT/00008 | S00008 | Coastal Workspace Outfitters | FL | Coastal Express | 14.4 | 13.5 | 2026-10-19
WH/OUT/00009 | S00009 | Blue Ridge Learning Supply | NC | Coastal Express | 24 | 13.5 | 2026-10-19